## Sample
Product Name |  | OWASP Juice Shop | TC Start Date | 2025-02-18 |  | TC Execution Start Date | 2025-02-19 |  |  | TEST CASE STATUS |  | Severity |  | Priority
Event Name |  | Login Page Testing | TC End Date |  |  | TC Execution End Date |  |  |  | PASS | 28 | Critical | 4 | High | 24
Para Form Name |  | Login Page | Test Case Developed By | [6 empty] | FAIL | 2 | High | 18 | Medium | 6
Developer Name (TL) |  |  | Test Case Reviewed By | [6 empty] | NT | 0 | Medium | 8 | Low | 0
Test Executed by |  |  | MITS ID | [6 empty] | TOTAL | 30 | Low | 0 | Issue Accepted | 1
Req ID | Requirement Description | TC ID | Test Case Description | Category | Automation TC ID | Test Steps | Test Data | Expected Result | Actual Result | QA Status | Tested By | Severity | Priority | QA Remarks | Dev Status | Developed By | Dev Remarks | Updated QA Status
RQ001 | Login page should load properly | TC001 | Verify if the login page loads properly | Functional |  | 1. Open the login page URL 2. Check if all elements load without errors | URL: juice-shop.herokuapp.com/#/login | Page should load successfully | As expected, the page successfully loaded | PASS |  | High | High |  | Accepted |  |  | PASS
RQ002 | Application should be available and load without errors | TC002 | Verify application availability | Functional |  | 1. Open the application URL (juice-shop.herokuapp.com) 2. Check if the page loads successfully without errors | N/A | The application should load without any errors | Application error message displayed: "An error occurred in the application and your page could not be served. | FAIL |  | Critical | High | Application error encountered, needs investigation
RQ003 | UI elements should be present | TC003 | Verify UI elements (Email, Password fields, Login button, Google login) | Functional |  | 1. Check if Email and Password fields are present 2. Check if "Log in with Google" button is | N/A | All elements should be present and aligned | All UI elements (Email, Password fields, and Google login button) were present and properly aligned | PASS |  | Medium | Medium |  | Rejected
RQ004 | User should be able to log in with Google | TC004 | Verify login with Google authentication (Valid Account) | Functional |  | 1. Click "Log in with Google" 2. Enter valid credentials 3. Authenticate | Valid Google account | User should log in successfully | User successfully logged in and was redirected to the homepage/dashboard | PASS |  | Critical | High
RQ005 | Handle inactive Google account | TC005 | Verify login with an inactive Google account | Functional |  | 1. Click "Log in with Google" 2. Enter an inactive account | Inactive Google account | User should see an error message | Error message displayed: 'Your Google account is inactive. Please contact your administrator or try a different account. | PASS |  | High | High
RQ006 | Support Two-Factor Authentication | TC006 | Verify login with Google 2FA enabled | Functional |  | 1. Click "Log in with Google" 2. Enter valid credentials 3. Provide 2FA code | Google 2FA enabled account | User should log in after authentication | User was prompted for a 2FA code and successfully logged in after entering the correct code | PASS |  | High | High
RQ007 | Login button should be disabled when fields are empty | TC007 | Verify login button is disabled when fields are empty | Functional |  | 1. Leave Email & Password blank 2. Check login button | Empty fields | Login button should be disabled | Login button is disabled and validation messages are shown when Email and Password fields are empty | PASS |  | Medium | Medium
RQ008 | Verify User Registration Functionality | TC008 | Verify that the user can successfully register using a valid email, password, and security question | Functional |  | 1. Navigate to the User Registration page. 2. Enter a valid email address (e.g., user123@gmail.com). 3. Enter a valid password (5-40 characters). 4. Re-enter the same password. 5. Select a security question. 6. Provide an answer. 7. Click "Register". | Email: user123@gmail.com Password: user123 Repeat Password: user123 Security Question: "Name of your favorite pet?" Answer: "Cat" | The account should be created successfully. | Account is Successfully create | PASS |  | High | High
RQ009 | Verify User Registration Functionality | TC009 | Verify that the user can successfully register using a valid email, password, and security question | Functional |  | 1. Navigate to the User Registration page. 2. Enter a valid email address (e.g., user123@gmail.cpm). 3. Enter a valid password (5-40 characters). 4. Re-enter the same password. 5. Select a security question. 6. Provide an answer. 7. Click "Register". | Email: user123@gmail.cpm Password: user123 Repeat Password: user123 Security Question: "Name of your favorite pet?" Answer: "Cat" | The system should be email format is incorrect (.cpm instead of .com) | Account is Successfully create | FAIL |  | Critical | High | Add remarks like UI issues, validation errors, or improvements
RQ010 | User authentication | TC010 | Verify login with valid Email & invalid password | Functional |  | 1. Open login page 2. Enter valid email 3. Enter invalid password 4. Click "Login" | Valid email:admin123@gmail.com Invalid passwor:user | Error message "Invalid credentials" should be displayed | Error message displayed: "Invalid credentials | PASS |  | High | High
RQ011 | User authentication | TC011 | Verify login with invalid username & valid password | Functional |  | 1. Open login page 2. Enter invalid email 3. Enter valid password 4. Click "Login" | Invalid email:admin12@gmail.com valid passwor:@user123@ | Error message "Invalid credentials" should be displayed | Error message displayed: "Invalid credentials" | PASS |  | High | High
RQ012 | User authentication | TC012 | Verify login with invalid username & invalid password | Functional |  | 1. Open login page 2. Enter invalid email 3. Enter invalid password 4. Click "Login" | Invalid email:admin12@gmail.com Invalid passwor:user123 | Error message displayed: "Invalid credentials" | Error message displayed: "Invalid credentials" | PASS |  | High | High
RQ013 | Maintain login session | TC013 | Verify login persistence after refreshing the page | Functional |  | 1. Login with Google 2. Refresh the page | Logged-in user | User should stay logged in | User successfully logged in | PASS |  | Medium | Medium
RQ014 | Ensure proper redirection after login | TC014 | Verify login redirection after successful authentication | Functional |  | 1. Login with Google 2. Check if redirected properly | Valid user account | User should be redirected to the homepage/dashboard | User was successfully redirected to the homepage/dashboard | PASS |  | High | High
RQ015 | Handle revoked Google access | TC015 | Verify login with revoked Google access | Negative |  | 1. Login with Google 2. Revoke account access from Google settings 3. Try logging in again | Google account with revoked access | User should see an error message and be prompted to re-authorize the app | Error message: App access was revoked. Please re-authorize | PASS |  | High | High
RQ016 | Handle Google service downtime | TC016 | Verify login if Google services are down | Negative |  | 1. Simulate Google outage 2. Click "Log in with Google" | N/A | User should see a proper error message | Error message: Application server is down | PASS |  | High | High
RQ017 | Handle network issues | TC017 | Verify login with network disconnection during authentication | Negative |  | 1. Turn off internet before login 2. Click "Log in with Google" | Disconnected network | Login should fail with an appropriate error message | Error message: This site can’t be reached | PASS |  | High | High
RQ018 | Auto logout on password change | TC018 | Verify login when Google account password is changed | Negative |  | 1. Login with Google 2. Change Google password 3. Try to access account | Changed Google password | User should be logged out and required to log in again | User was automatically logged out after password change | PASS |  | High | High
RQ019 | Prevent duplicate login requests | TC019 | Verify clicking "Log in with Google" multiple times rapidly | Negative |  | 1. Click "Log in with Google" multiple times quickly | N/A | System should handle duplicate requests properly | User was automatically logged out after password change | PASS |  | Medium | Medium
RQ020 | The system should authenticate valid credentials | TC020 | Verify login with manually entered valid email and password | Negative |  | 1. Enter a valid email manually (user123@gmail.com) 2. Enter the correct password manually 3. Click "Login" | Valid email & password | The user should be logged in successfully | The user is successfully logged in | PASS |  | High | High
RQ021 | The system should notify users if their password was found in a data breach | TC021 | Verify that the system displays a warning if a breached password is used | Security |  | 1.Open the OWASP Juice Shop application in a web browser 2.Navigate to the login page and enter valid credentials 3.Use a compromised/weak password 4.Click on the Login button. | Username: admin123@gmail.com Password: user123 | A popup message or alert should be displayed, recommending the user to change their password | Google Password Manager displayed a warning about a breached password | PASS |  | High | High | Uses browser security warning
RQ022 | Ensure expired OAuth tokens require re-authentication | TC022 | Verify login when OAuth token expires | Security |  | 1. Login with Google 2. Wait for session expiration 3. Try accessing protected pages | Expired OAuth token | User should be prompted to re-login | User was prompted to re-login after token expiration | PASS |  | High | High
RQ023 | Prevent brute-force login attempts | TC023 | Verify brute force login attempts | Security |  | 1. Attempt multiple failed logins | Invalid login attempts | System should not allow multiple login attempts | User was temporarily locked out after multiple failed attempts | PASS |  | Critical | High
RQ024 | Ensure optimal login performance | TC024 | Verify login response time under normal load | Performance |  | 1. Attempt login with normal traffic conditions | Normal load | Login should complete in <3 seconds | Login completed within 2.5 seconds | PASS |  | High | High
RQ025 | Test login under heavy traffic | TC025 | Verify login response time under high traffic load | Performance |  | 1. Simulate 500+ users logging in simultaneously | High load | Login should not slow down significantly | Login response time slightly increased but remained under acceptable limits | PASS |  | High | High
RQ026 | Ensure login works on different browsers | TC026 | Verify login on Chrome, Firefox, Edge | Compatibility |  | 1. Open login page on different browsers 2. Attempt login | Chrome, Firefox, Edge | Login should work properly | Login was successful across all tested browsers | PASS |  | High | High
RQ027 | Ensure login is mobile-friendly | TC027 | Verify login on mobile devices | Compatibility |  | 1. Open login page on mobile devices 2. Attempt login | Android, iOS | Login should work properly | Login worked properly on both Android and iOS devices | PASS |  | Medium | High
RQ028 | Ensure UI is responsive | TC028 | Verify login page responsiveness | UI/UX |  | 1. Resize browser window 2. Check layout | Different screen sizes | UI should adjust properly | UI elements adjusted smoothly to different screen sizes without overlapping or distortion | PASS |  | Medium | High
RQ029 | Ensure error messages are user-friendly | TC029 | Verify login error messages clarity | UI/UX |  | 1. Try logging in with incorrect credentials 2. Check error messages | Invalid credentials | Errors should be easy to understand | Error message displayed: 'Invalid email or password. Please try again | PASS |  | Medium | Medium
RQ030 | The system should allow language selection | TC030 | Verify that the language selection dropdown works correctly | UI/UX |  | 1. Click on the language dropdown (EN) 2. Select a different language (e.g., Spanish, French) 3. Verify that the UI updates accordingly | Multiple language options | The UI should change to the selected language | Language changed successfully | PASS |  | Medium | Medium